## Development Efforts
# | Task | Decomposition Item |  | Comments | Dependencies | Optimistic (man/days) | Pessimistic (man/days) | Mosk Likely (man/days) | Expected (man/days) | Standard Deviation (Individual) | Variance (Standard Deviation Squared) | Documentation (man/days) | Unit Testing (man/days) | Code Review (man/days) | Defect Fixing (man/days) | Comertional Adjustment Factors | Comertial Final Expected (man/days) | Educational Adjustment Factors | Educational Final Expected (man/days)
0 | Configuration
1 | Install and confugure RDBMS |  | DB |  |  | 0.25 | 1 | 0.5 | 0.54167 | 0.125 | 0.015625 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
2 | Install and configure DB management tool |  | DB |  |  | 0.1 | 0.5 | 0.25 | 0.26667 | 0.066667 | 0.0044444 | 0.04 | 0 | 0.053333 | 0.066667 | 1.29 | 0.5504 | 5.078 | 2.1666
3 | Install and configure data integration tool |  | DB |  |  | 0.25 | 1 | 0.5 | 0.54167 | 0.125 | 0.015625 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
4 | Git configuration |  | DB |  |  | 0.25 | 1 | 0.5 | 0.54167 | 0.125 | 0.015625 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
1 | Create an Entity-Relationship Diagram (ERD) for Operational DB based on the identified entities and relationships.
1 | Identify the entities that need to be represented in the database. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 | Analyze the relationships between the entities. |  | DB |  |  | 0.5 | 1 | 1 | 0.92 | 0.083333 | 0.0069444 | 0.138 | 0 | 0.184 | 0.23 | 1.29 | 1.8989 | 5.078 | 7.4748
3 | Identify the attributes associated with each entity. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
4 | Choose data types for entities. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
5 | Determine primary key for each entity. |  | DB |  |  | 0.5 | 1 | 1 | 0.92 | 0.083333 | 0.0069444 | 0.138 | 0 | 0.184 | 0.23 | 1.29 | 1.8989 | 5.078 | 7.4748
6 | Normalize the data model to minimize redundancy and improve efficiency. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Create an Entity-Relationship Diagram (ERD) for Raw Data DB based on the identified entities and relationships.
1 | Identify the entities that need to be represented in the database. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
2 | Analyze the relationships between the entities. |  | DB |  |  | 0.25 | 0.5 | 0.5 | 0.46 | 0.041667 | 0.0017361 | 0.069 | 0 | 0.092 | 0.115 | 1.29 | 0.94944 | 5.078 | 3.7374
3 | Identify the attributes associated with each entity. |  | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
4 | Choose data types for entities. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
5 | Determine primary key for each entity. |  | DB |  |  | 0.25 | 0.5 | 0.5 | 0.46 | 0.041667 | 0.0017361 | 0.069 | 0 | 0.092 | 0.115 | 1.29 | 0.94944 | 5.078 | 3.7374
6 | Normalize the data model to minimize redundancy and improve efficiency. |  | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
3 | Create data dictionary for Operational DB according to ERD.
1 | Describe entities related to articles. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
2 | Describe entities related to videos. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
3 | Describe entities related to comments. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
4 | Describe entities related to publication categories. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
5 | Describe entities related to users’ data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
6 | Describe entities related to authors of publications. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
7 | Describe entities related to publication partners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
8 | Describe entities related to surveys. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
9 | Describe entities related to social network data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
10 | Describe entities related to banners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
11 | Describe entities related to advertisement. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
12 | Describe entities related to users’ subscription. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
13 | Describe entities related to additional entities that were identified during DB modeling. |  | DB |  |  | 0.5 | 0.75 | 0.5 | 0.54167 | 0.041667 | 0.0017361 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
4 | Create data dictionary for Raw Data DB according to ERD.
1 | Describe entities related to articles. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
2 | Describe entities related to article categories. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
3 | Describe entities related to users’ data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
4 | Describe entities related to partners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
5 | Describe entities related to additional entities that were identified during DB modeling. |  | DB |  |  | 0.5 | 0.75 | 0.5 | 0.54167 | 0.041667 | 0.0017361 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
5 | Create Operational DB according to ERD and data dictionary.
1 | Create Operational DB. |  | DB |  |  | 0.1 | 0.25 | 0.1 | 0.125 | 0.025 | 0.000625 | 0.01875 | 0 | 0.025 | 0.03125 | 1.29 | 0.258 | 5.078 | 1.0156
2 | Create entities related to articles. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
3 | Create entities related to videos. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
4 | Create entities related to comments. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
5 | Create entities related to publication categories. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
6 | Create entities related to users’ data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
7 | Create entities related to authors of publications. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
8 | Create entities related to publication partners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
9 | Create entities related to surveys. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
10 | Create entities related to social network data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
11 | Create entities related to banners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
12 | Create entities related to advertisement. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
13 | Create entities related to users’ subscription. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
14 | Create entities related to additional entities that were identified during DB modeling. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
6 | Create Raw data DB according to ERD and data dictionary.
1 | Create entities related to articles. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
2 | Create entities related to article categories. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
3 | Create entities related to users’ data. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
4 | Create entities related to partners. |  | DB |  |  | 0.25 | 0.5 | 0.25 | 0.29167 | 0.041667 | 0.0017361 | 0.04375 | 0 | 0.058333 | 0.072917 | 1.29 | 0.602 | 5.078 | 2.3697
5 | Create entities related to additional entities that were identified during DB modeling. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
7 | Generate test data set for Operational DB.
1 | Generate data related to articles. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 | Generate data related to videos. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
3 | Generate data related to comments. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
4 | Generate data related to publication categories. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
5 | Generate data related to users. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
6 | Generate data related to authors of publications. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
7 | Generate data related to publication partners. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
8 | Generate data related to surveys. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
9 | Generate data related to social networks. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
10 | Generate data related to banners. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
11 | Generate data related to advertisement. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
12 | Generate data related to users’ subscription. |  | DB |  |  | 0.5 | 1 | 0.5 | 0.58333 | 0.083333 | 0.0069444 | 0.0875 | 0 | 0.11667 | 0.14583 | 1.29 | 1.204 | 5.078 | 4.7395
13 | Generate data related to additional entities that were identified during DB modeling. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
8 | Implement logging in Operational DB.
1 | Implement functionality to log any data changes into a specific DB table (CDC). |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Implement functionality to log any errors and failures into a specific DB table. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
9 | Maintain navigation on the portal
1 | Implement functionality to add/edit/delete data related to publication categories (sports, leagues, teams). | Allow admin users to add a new team on the portal | DB | Implement functionality to add/edit/delete data related to publication categories (sports, leagues, teams). |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow admin users to edit the existing team
3 |  | Allow admin users to delete the existing team
10 | Log in and sign up to the portal
1 | Implement functionality to add data related to users. | Allow users to sign up on the portal using an email | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Add admin account to the portal
3 | Implement functionality to store users’ activity. | Allow users to log in to the portal using an email | DB | Implement functionality to store users’ activity. |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
4 |  | Allow admin user to log in to the portal using an email
11 | Site languages on the portal
1 | Implement functionallity to store data about portal languages. | Allow admin user to configure site languages on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow users to change a site language on the portal
3 |  | Allow admin user to change a site language on the portal
12 | Manage articles on the portal
1 | Implement functionality to add/edit/delete data related to articles. | Allow admin users to add a new article | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
2 |  | Allow admin users to edit an existing article
3 |  | Allow admin users to publish and unpublish an existing article
4 |  | Allow admin users to move an existing article between categories
5 |  | Allow admin users to delete an existing article
7 | Implement functionallity to store media data. | Allow admin users to have advanced editor of the article image - image update | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
8 |  | Allow admin users to have advanced editor of the article image - image deletion
9 |  | Allow admin users to have advanced editor of the article image - image crop
10 |  | Allow admin users to have advanced editor of the article image - image resize
11 |  | Allow admin users to have advanced editor of the article image - image filters
12 |  | Add and configurate image uplod on the portal
13 | Home page of the portal
1 | Implement functionality to add/edit/delete data related to Main articles section. | Allow admin user to configure the Main articles section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Implement functionality to add/edit/delete data related to Breakdown section. | Allow admin user to configure the Breakdown section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
3 | Implement functionality to add/edit/delete data related to Photo of the day section. | Allow admin user to configure the Photo of the day section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
4 | Implement functionality to add/edit/delete data related to Home page section. | Allow admin user to preview the Home page | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
14 | Social networks on the portal | Social networks on the portal
1 | Implement functionality to add/edit/delete data related to social networks. | Allow admin user to configure social networks for sharing | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
2 |  | Allow admin user to configure social networks for following
3 | Implement functionality to store social networks tokens. | Allow admin user to configure social networks for sign up and log in | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
4 |  | Allow users to log in to the portal using a third-party authentication provider
5 | Implement functionality to add/edit/delete data related to social networks activities. | Allow users to share Sports Hub portal on social networks | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
6 |  | Allow users to follow the portal on social networks
7 |  | Allow users to share an article from the portal
8 | Purge social network activity history once in 90 days. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
9 | Retrieve the number of shares for each article and video on social networks. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
10 | Retrieve the percentage of users who shared publications on social media. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
11 | Retrieve number of publications shared on social networks by each user. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
12 | Retrieve total number of each publication shared on social networks. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
13 | Retrieve number of articles and videos shares per each social network. |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
15 | Site footer of the portal
1 | Implement functionality to add/edit/delete data related to footer configuration. | Allow admin user to configure site footer | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 1.6 | 5.078 | 8.1248
2 |  | Allow users view site footer on the portal
16 | Comments block on the portal
1 | Implement functionality to enable/disable ability to comment on an article. | Allow users to comment an article on the portal | DB |  |  | 0.25 | 1 | 0.5 | 0.54167 | 0.125 | 0.015625 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
2 | Implement functionality to add/edit/delete data related to comments. | Allow users to interact with existing article comments on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
3 | Retrieve the ratio of positive to negative comments for each article |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
4 | Retrieve the number of replies for each comment of each article and video |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
5 | Retrieve the number of comments left by each user |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
17 | The most popular and commented articles on the portal
1 | Implement functionality to add/edit/delete data related to Most popular section. | Allow admin user to configure the Most popular section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Implement functionality to add/edit/delete data related to Most commented section. | Allow admin user to configure the Most commented section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
3 | Retrieve the number of views of each article and video per day/week/month. | Allow site users to view the most popular articles | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
4 | Retrieve the number of comments for each article and video. | Allow site users to view the most commented articles | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
18 | Lifestyle and Dealbook news
1 | Implement functionality to add/edit/delete data about Lifestyle and Dealbook articles. | Allow admin users to add new articles to Lifestyle and Dealbook | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
2 |  | Allow admin users to edit Lifestyle and Dealbook's articles | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
3 |  | Allow admin users to publish/unpublish Lifestyle and Dealbook's articles
4 |  | Allow admin users to delete Lifestyle and Dealbook's articles | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
19 | Sports videos on the portal
1 | Implement functionality to add/edit/delete data related to videos. | Allow admin users to add new videos | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 |  | Allow admin users to publish/unpublish existing videos
3 |  | Allow admin users to edit existing videos
4 |  | Allow admin users to delete existing videos
5 | Implement functionality to enable/disable ability to share a video. | Allow site users to share videos on social networks | DB |  |  | 0.25 | 1 | 0.5 | 0.54167 | 0.125 | 0.015625 | 0.08125 | 0 | 0.10833 | 0.13542 | 1.29 | 1.118 | 5.078 | 4.4009
20 | User personal cabinet
1 | Implement functionality to edit data related to users. | Allow users to update their personal information | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow users to change their password via profile
21 | Team hub: news about favorite teams
1 | Implement functionality to add/edit/delete data related to Team Hub. | Allow users to manage favorite teams in the personal cabinet | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
2 |  | Allow users to see the Team hub page
3 |  | Allow users to see teams news on Team hub based on their geolocation
22 | Manage news partners on the portal
1 | Implement functionality to add/edit/delete data related to partners. | Allow admin user to configure new partners on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow admin user to edit existing partners' configurations on the portal
3 |  | Allow admin user to activate and deactivate news partners
4 |  | Allow admin user to edit news from partners
5 |  | Allow admin user to delete news from partners
6 | Create ETL workflow to process data from partner’s source |  | DB |  |  | 5 | 7 | 6 | 6 | 0.33333 | 0.11111 | 0.9 | 0 | 1.2 | 1.5 | 1.29 | 12.384 | 5.078 | 48.7488
7 | Create ETL workflow to migrate partner's data from Raw DB to the Operational DB |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
8 | Create error handling and alerting strategy for ETL solutions |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
9 | Implement data quality checks and validation processes |  | DB |  |  | 3 | 5 | 4 | 4 | 0.33333 | 0.11111 | 0.6 | 0 | 0.8 | 1 | 1.29 | 8.256 | 5.078 | 32.4992
10 | Set up automatic execution of ETL processes according to schedules |  | DB |  |  | 0.5 | 1 | 1 | 0.91667 | 0.083333 | 0.0069444 | 0.1375 | 0 | 0.18333 | 0.22917 | 1.29 | 1.892 | 5.078 | 7.4477
23 | Newsletter subscription
1 | Implement functionality to store configuration of Newsletter footer section. | Allow admin user to configure Newsletter footer section | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Implement functionality to store configuration of users subscriptions. | Allow users to subscribe to newsletter | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
24 | User management on the portal
1 | Implement functionality to edit data related to users. | Allow admin user to block users on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow admin user to activate users on the portal
3 |  | Allow admin user to give user admin permissions on the portal
4 |  | Allow admin user to remove admin permissions from users on the portal
5 | Implement functionality to delete data related to users | Allow admin user to delete users on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
6 | Notify administrators of any suspicious or unusual user activity |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
7 | Export users’ activity data for requested period in CSV or Excel file |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
8 | Allow users viewing their own activity history, including past logins, content creation and modification |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
9 | Purge users’ activity data once in 90 days |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
10 | Retrieve the percentage of users who have created an account but have never logged in |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
11 | Retrieve information about how many new users sign up on website each week |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
12 | Retrieve duration of each session of each user on the website |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
13 | Retrieve information about users who have logged in for more than 1 hour |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
14 | Retrieve users who have not logged in to website in the last 30 days |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
25 | Banners on the portal
1 | Implement functionality to add/edit/delete data related to banners. | Allow admin users to configure banners on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow admin users to configure predefined banners on the portal
26 | Manage advertisements on the portal
1 | Implement functionality to add/edit/delete data related to advertisement. | Allow admin user to configure advertisements | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
3 | Store data about users’ views of advertisements |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
4 | Purge history of advertisement views once in 90 days |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
5 | Retrieve number of advertisements’ views per day/week/month |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
27 | Surveys on the portal
1 | Implement functionality to add/edit/delete data related to surveys. | Allow admin to create surveys on the portal | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
2 |  | Allow admin to publish surveys
3 |  | Allow admin to close surveys
4 | Implement functionality to store surveys answers in the appropriate DB tables. | Allow users to participate in surveys on news pages | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
5 | Retrieve number of responses per survey |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
6 | Retrieve number of surveys completed by each user |  | DB |  |  | 0.25 | 0.75 | 0.5 | 0.5 | 0.083333 | 0.0069444 | 0.075 | 0 | 0.1 | 0.125 | 1.29 | 1.032 | 5.078 | 4.0624
28 | Implement non-functional requirements for Operational DB.
1 | Analyze query execution plans and optimize queries for better response time. |  | DB |  |  | 0.5 | 1 | 1 | 0.91667 | 0.083333 | 0.0069444 | 0.1375 | 0 | 0.18333 | 0.22917 | 1.29 | 1.892 | 5.078 | 7.4477
2 | Implement indexing strategies to enhance query performance. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
3 | Fine-tune database configuration settings for optimal performance. |  | DB |  |  | 0.5 | 1.5 | 1 | 1 | 0.16667 | 0.027778 | 0.15 | 0 | 0.2 | 0.25 | 1.29 | 2.064 | 5.078 | 8.1248
4 | Implement data archiving or purging mechanisms to manage data growth and optimize performance. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
5 | Set up comprehensive monitoring for the database, including deadlocks, performance metrics, resource utilization, and workload patterns. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
6 | Implement backup strategy. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
7 | Implement role-based access control and user management. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
8 | Identify sensitive data. |  | DB |  |  | 0.5 | 1 | 0.75 | 0.75 | 0.083333 | 0.0069444 | 0.1125 | 0 | 0.15 | 0.1875 | 1.29 | 1.548 | 5.078 | 6.0936
9 | Protect sensitive data with encryption a row-level security. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
29 | Implement data warehouse solution.
1 | Determine the appropriate architecture for the data warehouse, such as a star schema, snowflake schema, or hybrid approach. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
2 | Define the dimensions, facts, and hierarchies that will structure the data warehouse. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
3 | Create ERD for DWH according to the chosen architecture. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
4 | Create DWH objects according to ERD. |  | DB |  |  | 1 | 2 | 1 | 1.1667 | 0.16667 | 0.027778 | 0.175 | 0 | 0.23333 | 0.29167 | 1.29 | 2.408 | 5.078 | 9.4789
5 | Design Slowly Changing Dimension (SCD) strategies. |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
6 | Design and implement the incremental load process to load only the changes since the last update. |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
7 | Develop the full load process to load the entire dataset from the source systems into the data warehouse when needed. |  | DB |  |  | 1 | 3 | 2 | 2 | 0.33333 | 0.11111 | 0.3 | 0 | 0.4 | 0.5 | 1.29 | 4.128 | 5.078 | 16.2496
8 | Design and develop the ETL processes to extract data from source systems. |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
9 | Implement indexes strategy. |  | DB |  |  | 1 | 2 | 1.5 | 1.5 | 0.16667 | 0.027778 | 0.225 | 0 | 0.3 | 0.375 | 1.29 | 3.096 | 5.078 | 12.1872
10 | Implement partitioning strategy. |  | DB |  |  | 2 | 4 | 3 | 3 | 0.33333 | 0.11111 | 0.45 | 0 | 0.6 | 0.75 | 1.29 | 6.192 | 5.078 | 24.3744
Total | [5 empty] | 93.95 | 216.25 | 149.35 | 151.2767 | 20.3833 | 3.979 | 22.6915 | 0 | 30.2553 | 37.8192 |  | 311.771 |  | 1229.0922
Standard Complex Deviation | [16 empty] | 1.9948
Final Recommended Estimate (man/days) | [16 empty] | 315.7605 |  | 1233.0817
Final Optimistic Estimate (man/days) | [15 empty] | 150.32
Final Pessimistic Estimate (man/days) | [15 empty] | 327.655

## Total Efforts - Autocalculated
Comercial Project
Total Dev Efforts (man/days) | QC Efforts (man/days)
315.7605 | 63.1521
Training Project
Total Dev Efforts (man/days) | QC Efforts (man/days)
1233.0817 | 246.6163

## Input Data
Activity Type | % from efforts on implementation
Documentation | 15%
Unit Testing | 0%
Code Review | 20%
Bug Fixing | 25%
Activity Type | % from dev efforts
Documentation | 20%
Manual Testing | 20%

## Adjustment Factors
Factor | Influence | Project Type |  | Observation
|  | Comercial Project | Training Project
Business Area Experience | 1.51 | NO | NO | Teams that aren't familiar with the project's business area need significantly more time. This shouldn't be a surprise.
Architecture and Risk Resolution | 1.38 | NO | NO | The more actively the project attacks risks, the lower the effort and cost will be. This is one of the few Cocomo II factors that is controllable by the project manager.
Database Size | 1.42 | NO | NO | Large, complex databases require more effort project-wide. Total influence is moderate.
Developed for Reuse | 1.31 | NO | NO | Software that is developed with the goal of later reuse can increase costs as much as 31%. This doesn't say whether the initiative actually succeeds. Industry experience has been that forward-looking reuse programs often fail.
Extent of Documentation Required | 1.52 | NO | NO | Too much documentation can negatively affect the whole project. Impact is moderately high.
Language and Tools Experience | 1.43 | NO | YES | Teams that have experience with the programming language and/or tool set work moderately more productively than teams that are climbing a learning curve. This is not a surprise.
Multi-Site Development | 1.56 | NO | NO | Projects conducted by a team spread across multiple sites around the globe will take 56% more effort than projects that are conducted by a team co-located at one facility. Projects that are conducted at multiple sites, including out-sourced or offshore projects, need to take this effect seriously.
Personnel Continuity (turnover) | 1.59 | NO | NO | Project turnover is expensive—in the top one-third of influential factors.
Platform Experience | 1.4 | NO | YES | Experience with the underlying technology platform affects overall project performance moderately.
Platform Volatility | 1.49 | NO | NO | If the platform is unstable, development can take moderately longer. Projects should weigh this factor in their decision about when to adopt a new technology. This is one reason that systems projects tend to take longer than applications projects.
Precedentedness | 1.33 | NO | NO | Refers to how "precedented" (we usually say "unprecedented") the application is. Familiar systems are easier to create than unfamiliar systems.
Process Maturity | 1.43 | NO | YES | Projects that use more sophisticated development processes take less effort than projects that use unsophisticated processes. Cocomo II uses an adaptation of the CMM process maturity model to apply this criterion to a specific project.
Product Complexity | 2.38 | NO | NO | Product complexity (software complexity) is the single most significant adjustment factor in the Cocomo II model. Product complexity is largely determined by the type of software you're building.
Programmer Capability (general) | 1.76 | NO | NO | The skill of the programmers has an impact of a factor of almost 2 on overall project results.
Required Reliability | 1.54 | NO | NO | More reliable systems take longer. This is one reason (though not the only reason) that embedded systems and life-critical systems tend to take more effort than other projects of similar sizes. In most cases, your marketplace determines how reliable your software must be. You don't usually have much latitude to change this.
Requirements Analyst Capability | 2 | NO | NO | The single largest personnel factor—good requirements capability—makes a factor of 2 difference in the effort for the entire project. Competency in this area has the potential to reduce a project's overall effort from nominal more than any other factor.
Requirements Flexibility | 1.26 | NO | NO | Projects that allow the development team latitude in how they interpret requirements take less effort than projects that insist on rigid, literal interpretations of all requirements.
Storage Constraint | 1.46 | NO | NO | Working on a platform on which you're butting up against storage limitations moderately increases project effort.
Team Cohesion | 1.29 | YES | YES | Teams with highly cooperative interactions develop software more efficiently than teams with more contentious interactions.
Time Constraint | 1.63 | NO | NO | Minimizing response time increases effort across the board. This is one reason that systems projects and real-time projects tend to consume more effort than other projects of similar sizes.
Use of Software Tools | 1.5 | NO | NO | Advanced tool sets can reduce effort significantly.
Localization | 1.1 | NO | YES | Support of each additional Locale requires +10% for each screen implementation
Multi-Web Browsers support | 1.25 | NO | YES | Support of each additional Web browser requires +25% to effors planned for client side implementation (javascript code, CSS,...)
Data Complexity | 1.25 | NO | YES | The complexity of the data model and structure, data volume, and data sources can significantly impact the efforts required for building the DB systems and ETL processes.
|  | Project Type |  | Observation
|  | Comercial Project | Training Project
Combined factors |  | 1.29 | 5.078
|  | Averaging the factors (softer approach) smooths their impact by treating each one with equal weight | Multiplying all factors (conservative approach) amplifies risk by compounding all adjustment factors together